## Sheet1
Tanggal | No. Docket | Kontraktor | Nama Proyek | Homebase | Nama Mutu | Slump | TM | Driver | Plant Utama | Plant Produksi | Volume Kirim | Volume Terima | Is Retail | Waktu Kirim | Waktu Terima | Docket Fisik | Status | Invoiced
2026-09-25 | DOCKET/PTB/09-2026/10848 | HK - JAKON JO / BARRIER PE2 - AE2 BRIDGE 17 STA 30+600 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DATA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 944 | GALANG PRASETYA HIDAYAH | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 18:56:02 | 2026-09-25 20:01:21 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10849 | HK - JAKON JO / BARRIER PE2 - AE2 BRIDGE 17 STA 30+600 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DATA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 631 | RIYAN | Plant Patimban | Plant Patimban | 6 | 6 | Bukan | 2026-09-25 20:04:25 | 2026-09-26 02:43:56 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10842 | HK - JAKON JO / HALFSLAB S1 (6 UNIT) PS.14 STA 31+000 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DENI | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 631 | RIYAN | Plant Patimban | Plant Patimban | 6 | 6 | Bukan | 2026-09-25 16:10:40 | 2026-09-25 18:05:23 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10844 | HK - JAKON JO / HALFSLAB S1 (6 UNIT) PS.14 STA 31+000 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DENI | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 852 | NANO SUWARNO | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 17:20:13 | 2026-09-25 18:05:30 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10827 | HK - JAKON JO / LC DETOUR OP.6 STA 32+048 / CLASS E / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | EGI | Class E-1 FA | Slump 12.0 +2.0/-2.0 | TM 880 | HATOMI | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 08:14:43 | 2026-09-25 10:50:59 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10828 | HK - JAKON JO / LC DETOUR OP.6 STA 32+048 / CLASS E / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | EGI | Class E-1 FA | Slump 12.0 +2.0/-2.0 | TM 456 | WARSID | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 08:35:52 | 2026-09-25 10:55:51 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10829 | HK - JAKON JO / LC DETOUR OP.6 STA 32+048 / CLASS E / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | EGI | Class E-1 FA | Slump 12.0 +2.0/-2.0 | TM 631 | RIYAN | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 08:41:59 | 2026-09-25 12:40:45 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10830 | HK - JAKON JO / LC DETOUR OP.6 STA 32+048 / CLASS E / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | EGI | Class E-1 FA | Slump 12.0 +2.0/-2.0 | TM 944 | TEGUH ARIFIANTO | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 08:52:42 | 2026-09-25 13:05:02 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10837 | HK - JAKON JO / LC DETOUR OP.6 STA 32+048 / CLASS E / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | EGI | Class E-1 FA | Slump 12.0 +2.0/-2.0 | TM 631 | RIYAN | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 13:08:41 | 2026-09-25 15:44:56 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10841 | HK - JAKON JO / LC DETOUR OP.6 STA 32+048 / CLASS E / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | EGI | Class E-1 FA | Slump 12.0 +2.0/-2.0 | TM 590 | CAHYUDIN AMZAH | Plant Patimban | Plant Patimban | 6 | 6 | Bukan | 2026-09-25 15:45:47 | 2026-09-25 18:05:36 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10850 | MURINDA / SLAB / K 400 / AD PTB | GA Warehouse Building of Vinfast Phase 2 Project | DENI | K-400 NFA | Slump 12.0 +1.5/-1.5 | TM 590 | UJANG SAPUTRA | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 20:34:13 | 2026-09-26 02:44:23 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10851 | MURINDA / SLAB / K 400 / AD PTB | GA Warehouse Building of Vinfast Phase 2 Project | DENI | K-400 NFA | Slump 12.0 +1.5/-1.5 | TM 852 | NANO SUWARNO | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 20:44:13 | 2026-09-26 02:44:31 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10845 | PP - TOL PTB / BOTTOM WING WALL R BOX CULVERT STA 16+683+ PENINGGI PARAPET OVERPASS STA 18+100 / FC 30 / AD PTB | JALAN TOL AKSES PATIMBAN | ARDIAN | Fc-30 NFA | Slump 12.0 +2.0/-2.0 | TM 687 | WAWAN SETIAWAN | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 17:34:44 | 2026-09-25 18:06:00 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10846 | PP - TOL PTB / BOTTOM WING WALL R BOX CULVERT STA 16+683+ PENINGGI PARAPET OVERPASS STA 18+100 / FC 30 / AD PTB | JALAN TOL AKSES PATIMBAN | ARDIAN | Fc-30 NFA | Slump 12.0 +2.0/-2.0 | TM 880 | TARMA | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 17:45:42 | 2026-09-25 18:06:06 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10847 | PP - TOL PTB / BOTTOM WING WALL R BOX CULVERT STA 16+683+ PENINGGI PARAPET OVERPASS STA 18+100 / FC 30 / AD PTB | JALAN TOL AKSES PATIMBAN | ARDIAN | Fc-30 NFA | Slump 12.0 +2.0/-2.0 | TM 648 | DACA MARWANTO | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 18:45:26 | 2026-09-26 02:44:03 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10838 | WIKA - ADHI JO / DS 1.1 STA 35+000 / CLASS D-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DENI | Class D-1 NFA | Slump 12.0 +2.0/-2.0 | TM 944 | GALANG PRASETYA HIDAYAH | Plant Patimban | Plant Patimban | 6 | 6 | Bukan | 2026-09-25 13:37:50 | 2026-09-25 15:38:32 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10840 | WIKA - ADHI JO / DS 1.1 STA 35+000 / CLASS D-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DENI | Class D-1 NFA | Slump 12.0 +2.0/-2.0 | TM 944 | GALANG PRASETYA HIDAYAH | Plant Patimban | Plant Patimban | 6 | 6 | Bukan | 2026-09-25 15:38:50 | 2026-09-25 16:35:02 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10839 | WIKA - ADHI JO / LC PLAT INJAK 35+803 / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | SUGENG | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 648 | DACA MARWANTO | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 15:24:31 | 2026-09-25 18:05:48 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10843 | WIKA - ADHI JO / LC PLAT INJAK 35+803 / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | SUGENG | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 944 | GALANG PRASETYA HIDAYAH | Plant Patimban | Plant Patimban | 5 | 5 | Bukan | 2026-09-25 16:37:11 | 2026-09-25 18:05:54 | Ada | Done | Belum
2026-09-25 | DOCKET/PTB/09-2026/10831 | WIKA - ADHI JO / MEDIAN DRAIN STA 36+000 / CLASS C-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DENI | Class C-1 NFA | Slump 12.0 +2.0/-2.0 | TM 648 | DODI IRAWAN | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-25 09:24:42 | 2026-09-25 13:15:36 | Ada | Done | Belum