## Sheet1
Tanggal | No. Docket | Kontraktor | Nama Proyek | Homebase | Nama Mutu | Slump | TM | Driver | Plant Utama | Plant Produksi | Volume Kirim | Volume Terima | Is Retail | Waktu Kirim | Waktu Terima | Docket Fisik | Status | Invoiced
2026-09-12 | DOCKET/PTB/09-2026/10081 | HK - JAKON JO / BARRIER A47 - A57 R/L PS.14 STA 30+800 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DENI | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 648 | DACA MARWANTO | Plant Patimban | Plant Patimban | 6 | 6 | Bukan | 2026-09-12 00:27:16 | 2026-09-12 02:00:06 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10126 | HK - JAKON JO / DECKSLAB PW2 - AW2 BRIGDGE 17 STA 30+700 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | AGUS | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 880 | HATOMI | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 20:18:27 | 2026-09-12 22:11:13 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10127 | HK - JAKON JO / DECKSLAB PW2 - AW2 BRIGDGE 17 STA 30+700 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | AGUS | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 852 | WAWAN SETIAWAN | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 20:26:48 | 2026-09-12 22:12:08 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10129 | HK - JAKON JO / DECKSLAB PW2 - AW2 BRIGDGE 17 STA 30+700 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | AGUS | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 648 | DODI IRAWAN | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 20:55:09 | 2026-09-12 23:02:21 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10134 | HK - JAKON JO / DECKSLAB PW2 - AW2 BRIGDGE 17 STA 30+700 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | AGUS | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 665 | HENDI SUPANDI | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 22:18:35 | 2026-09-12 23:42:43 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10135 | HK - JAKON JO / DECKSLAB PW2 - AW2 BRIGDGE 17 STA 30+700 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | AGUS | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 631 | AAM ADI ALAMSYAH | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 22:26:39 | 2026-09-13 00:14:52 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10139 | HK - JAKON JO / DECKSLAB PW2 - AW2 BRIGDGE 17 STA 30+700 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | AGUS | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 664 | OPIK | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 23:27:07 | 2026-09-13 00:41:33 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10140 | HK - JAKON JO / DECKSLAB PW2 - AW2 BRIGDGE 17 STA 30+700 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | AGUS | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 944 | UJANG SAPUTRA | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 23:38:14 | 2026-09-13 01:17:08 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10141 | HK - JAKON JO / DECKSLAB PW2 - AW2 BRIGDGE 17 STA 30+700 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | AGUS | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 903 | HERMAN SUHERMAN | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 23:48:01 | 2026-09-13 02:07:14 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10124 | PP - TOL PTB / APPROACH SLAB BOX CULVERT STA 16+060 / FC 30 / AD PTB | JALAN TOL AKSES PATIMBAN | TAUFIQ | Fc-30 NFA | Slump 12.0 +2.0/-2.0 | TM 664 | OPIK | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 19:31:48 | 2026-09-12 22:00:19 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10125 | PP - TOL PTB / APPROACH SLAB BOX CULVERT STA 16+060 / FC 30 / AD PTB | JALAN TOL AKSES PATIMBAN | TAUFIQ | Fc-30 NFA | Slump 12.0 +2.0/-2.0 | TM 944 | UJANG SAPUTRA | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 19:42:48 | 2026-09-12 22:00:24 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10082 | PP - TOL PTB / PILECAPE P2 B7 STA 20+000 / FC 30 / AD PTB | JALAN TOL AKSES PATIMBAN | AGUS | Fc-30 NFA | Slump 12.0 +2.0/-2.0 | TM 631 | WARSID | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 00:35:22 | 2026-09-12 04:33:03 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10083 | PP - TOL PTB / PILECAPE P2 B7 STA 20+000 / FC 30 / AD PTB | JALAN TOL AKSES PATIMBAN | AGUS | Fc-30 NFA | Slump 12.0 +2.0/-2.0 | TM 664 | CAHYUDIN AMZAH | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 00:47:23 | 2026-09-12 04:27:54 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10084 | PP - TOL PTB / PILECAPE P2 B7 STA 20+000 / FC 30 / AD PTB | JALAN TOL AKSES PATIMBAN | AGUS | Fc-30 NFA | Slump 12.0 +2.0/-2.0 | TM 852 | NANO SUWARNO | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 01:04:56 | 2026-09-12 07:06:14 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10086 | PP - TOL PTB / PILECAPE P2 B7 STA 20+000 / FC 30 / AD PTB | JALAN TOL AKSES PATIMBAN | AGUS | Fc-30 NFA | Slump 12.0 +2.0/-2.0 | TM 648 | DACA MARWANTO | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 02:23:21 | 2026-09-12 07:03:59 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10091 | PP - TOL PTB / PILECAPE P2 B7 STA 20+000 / FC 30 / AD PTB | JALAN TOL AKSES PATIMBAN | AGUS | Fc-30 NFA | Slump 12.0 +2.0/-2.0 | TM 664 | CAHYUDIN AMZAH | Plant Readymix Subang | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 08:22:01 | 2026-09-12 12:28:17 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10090 | TESCO INDOMARITIM / K 350 / AD PTB | PT Tesco Indomaritim | SUGENG | K-350 NFA | Slump 14.0 +2.0/-2.0 | TM 648 | DACA MARWANTO | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 07:20:17 | 2026-09-12 10:24:32 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10092 | TESCO INDOMARITIM / K 350 / AD PTB | PT Tesco Indomaritim | SUGENG | K-350 NFA | Slump 14.0 +2.0/-2.0 | TM 687 | TARMA | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 08:45:10 | 2026-09-12 11:15:42 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10093 | TESCO INDOMARITIM / K 350 / AD PTB | PT Tesco Indomaritim | SUGENG | K-350 NFA | Slump 14.0 +2.0/-2.0 | TM 852 | WAWAN SETIAWAN | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 08:58:00 | 2026-09-12 11:17:03 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10103 | TESCO INDOMARITIM / K 350 / AD PTB | PT Tesco Indomaritim | SUGENG | K-350 NFA | Slump 14.0 +2.0/-2.0 | TM 687 | ODAY | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 11:22:45 | 2026-09-12 13:48:50 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10105 | TESCO INDOMARITIM / K 350 / AD PTB | PT Tesco Indomaritim | SUGENG | K-350 NFA | Slump 14.0 +2.0/-2.0 | TM 648 | DODI IRAWAN | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 11:45:19 | 2026-09-12 14:19:35 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10106 | TESCO INDOMARITIM / K 350 / AD PTB | PT Tesco Indomaritim | SUGENG | K-350 NFA | Slump 14.0 +2.0/-2.0 | TM 664 | OPIK | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 12:29:31 | 2026-09-12 15:28:05 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10107 | TESCO INDOMARITIM / K 350 / AD PTB | PT Tesco Indomaritim | SUGENG | K-350 NFA | Slump 14.0 +2.0/-2.0 | TM 852 | WAWAN SETIAWAN | Plant Patimban | Plant Patimban | 7 | 7 | Bukan | 2026-09-12 12:38:25 | 2026-09-12 15:28:14 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10094 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 011 | OS 011 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 09:19:34 | 2026-09-12 10:13:26 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10095 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 003 | OS 003 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 09:30:30 | 2026-09-12 10:26:08 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10096 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 005 | OS 005 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 09:35:07 | 2026-09-12 10:26:39 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10097 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 015 | OS 015 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 09:40:34 | 2026-09-12 10:26:46 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10098 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 011 | OS 011 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 10:17:36 | 2026-09-12 11:27:10 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10100 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 003 | OS 003 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 10:31:02 | 2026-09-12 11:27:16 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10101 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 005 | OS 005 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 10:38:20 | 2026-09-12 11:29:08 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10102 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 015 | OS 015 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 10:44:34 | 2026-09-12 11:29:28 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10108 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 011 | OS 011 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 13:24:30 | 2026-09-12 14:19:02 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10109 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 003 | OS 003 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 13:34:50 | 2026-09-12 14:19:16 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10110 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 005 | OS 005 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 13:40:47 | 2026-09-12 15:27:44 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10112 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 015 | OS 015 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 14:18:37 | 2026-09-12 15:27:48 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10115 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 011 | OS 011 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 14:43:20 | 2026-09-12 15:27:52 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10116 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 003 | OS 003 | Plant Patimban | Plant Patimban | 10 | 10 | Bukan | 2026-09-12 14:49:07 | 2026-09-12 15:27:58 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10117 | WIKA - ADHI JO / STA 34+904 L1 / CTB 4% / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | CTB 4% NFA-0 NFA | Slump 0.0 +0.0/-0.0 | DT EXT 011 | OS 011 | Plant Patimban | Plant Patimban | 5 | 5 | Bukan | 2026-09-12 15:33:04 | 2026-09-12 17:52:05 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10113 | WIKA - ADHI JO / STA 35+625 L / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 687 | ODAY | Plant Patimban | Plant Patimban | 6 | 6 | Bukan | 2026-09-12 14:27:14 | 2026-09-12 17:48:55 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10114 | WIKA - ADHI JO / STA 35+625 L / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 648 | DODI IRAWAN | Plant Patimban | Plant Patimban | 6 | 6 | Bukan | 2026-09-12 14:35:58 | 2026-09-12 17:48:59 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10118 | WIKA - ADHI JO / STA 35+625 L / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 664 | OPIK | Plant Patimban | Plant Patimban | 5.5 | 5.5 | Bukan | 2026-09-12 16:22:07 | 2026-09-12 17:49:06 | Ada | Done | Belum
2026-09-12 | DOCKET/PTB/09-2026/10119 | WIKA - ADHI JO / STA 35+625 L / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 944 | UJANG SAPUTRA | Plant Patimban | Plant Patimban | 2.5 | 2.5 | Bukan | 2026-09-12 17:15:31 | 2026-09-12 17:49:17 | Ada | Done | Belum