## Sheet1
Tanggal | No. Docket | Kontraktor | Nama Proyek | Homebase | Nama Mutu | Slump | TM | Waktu Kirim
2026-05-20 | DOCKET/PTB/05-2026/03931 | HK - JAKON JO / DIAFRAGMA A1 - P1 OP 7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 967 | 2026-05-20 14:43:55
2026-05-20 | DOCKET/PTB/05-2026/03932 | HK - JAKON JO / DIAFRAGMA A1 - P1 OP 7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-05-20 14:45:41
2026-05-20 | DOCKET/PTB/05-2026/03909 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 944 | 2026-05-20 09:09:42
2026-05-20 | DOCKET/PTB/05-2026/03910 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-05-20 09:21:15
2026-05-20 | DOCKET/PTB/05-2026/03911 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 880 | 2026-05-20 09:31:03
2026-05-20 | DOCKET/PTB/05-2026/03912 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 782 | 2026-05-20 09:37:28
2026-05-20 | DOCKET/PTB/05-2026/03913 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 967 | 2026-05-20 09:47:23
2026-05-20 | DOCKET/PTB/05-2026/03914 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 701 | 2026-05-20 10:34:50
2026-05-20 | DOCKET/PTB/05-2026/03915 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-05-20 10:45:24
2026-05-20 | DOCKET/PTB/05-2026/03916 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 813 | 2026-05-20 10:59:03
2026-05-20 | DOCKET/PTB/05-2026/03917 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 687 | 2026-05-20 11:01:57
2026-05-20 | DOCKET/PTB/05-2026/03918 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 944 | 2026-05-20 11:25:06
2026-05-20 | DOCKET/PTB/05-2026/03919 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-05-20 11:33:15
2026-05-20 | DOCKET/PTB/05-2026/03920 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 880 | 2026-05-20 11:39:53
2026-05-20 | DOCKET/PTB/05-2026/03921 | HK - JAKON JO / PIERHEAD P1' STG. 3 (BACKWALL) BRIDGE 19 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 782 | 2026-05-20 12:48:42
2026-05-20 | DOCKET/PTB/05-2026/03896 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DENI | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 687 | 2026-05-20 00:18:27
2026-05-20 | DOCKET/PTB/05-2026/03898 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 811 | 2026-05-20 00:38:49
2026-05-20 | DOCKET/PTB/05-2026/03899 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-05-20 00:50:06
2026-05-20 | DOCKET/PTB/05-2026/03900 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 880 | 2026-05-20 01:10:08
2026-05-20 | DOCKET/PTB/05-2026/03901 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-05-20 01:19:21
2026-05-20 | DOCKET/PTB/05-2026/03902 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 813 | 2026-05-20 01:29:07
2026-05-20 | DOCKET/PTB/05-2026/03903 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 944 | 2026-05-20 01:44:23
2026-05-20 | DOCKET/PTB/05-2026/03904 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 967 | 2026-05-20 01:58:42
2026-05-20 | DOCKET/PTB/05-2026/03905 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 687 | 2026-05-20 02:08:22
2026-05-20 | DOCKET/PTB/05-2026/03906 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 811 | 2026-05-20 02:52:19
2026-05-20 | DOCKET/PTB/05-2026/03907 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 813 | 2026-05-20 05:15:39
2026-05-20 | DOCKET/PTB/05-2026/03908 | HK - JAKON JO / TOP SLAB P1' - P2' BRIDGE 20 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Fc-30 FA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-05-20 05:20:54
2026-05-20 | DOCKET/PTB/05-2026/03897 | PENTA OCEAN-TOYO-RINKAI-PP-WIKA-JAKON CONSORTIUM | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | Homebase 8 | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 782 | 2026-05-20 00:32:16
2026-05-20 | DOCKET/PTB/05-2026/03949 | PTRPWJ / PC SLAB PAV - 13739 / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DATA | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 894 | 2026-05-20 19:33:43
2026-05-20 | DOCKET/PTB/05-2026/03955 | PTRPWJ / PC SLAB PAV - 13739 / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DATA | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 782 | 2026-05-20 20:29:18
2026-05-20 | DOCKET/PTB/05-2026/03935 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-05-20 16:28:07
2026-05-20 | DOCKET/PTB/05-2026/03936 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 782 | 2026-05-20 16:37:12
2026-05-20 | DOCKET/PTB/05-2026/03938 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-05-20 17:18:47
2026-05-20 | DOCKET/PTB/05-2026/03939 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-05-20 17:42:51
2026-05-20 | DOCKET/PTB/05-2026/03940 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 701 | 2026-05-20 17:47:54
2026-05-20 | DOCKET/PTB/05-2026/03942 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 894 | 2026-05-20 17:58:31
2026-05-20 | DOCKET/PTB/05-2026/03943 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-05-20 18:15:37
2026-05-20 | DOCKET/PTB/05-2026/03944 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 782 | 2026-05-20 18:22:53
2026-05-20 | DOCKET/PTB/05-2026/03945 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-05-20 18:33:29
2026-05-20 | DOCKET/PTB/05-2026/03946 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-05-20 18:41:10
2026-05-20 | DOCKET/PTB/05-2026/03947 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | SUGENG | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-05-20 18:48:38
2026-05-20 | DOCKET/PTB/05-2026/03948 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-05-20 19:03:55
2026-05-20 | DOCKET/PTB/05-2026/03950 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 701 | 2026-05-20 19:39:59
2026-05-20 | DOCKET/PTB/05-2026/03951 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-05-20 19:55:13
2026-05-20 | DOCKET/PTB/05-2026/03952 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-05-20 20:05:39
2026-05-20 | DOCKET/PTB/05-2026/03953 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-05-20 20:12:25
2026-05-20 | DOCKET/PTB/05-2026/03954 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-05-20 20:18:24
2026-05-20 | DOCKET/PTB/05-2026/03956 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-05-20 20:38:42
2026-05-20 | DOCKET/PTB/05-2026/03957 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 894 | 2026-05-20 21:07:17
2026-05-20 | DOCKET/PTB/05-2026/03958 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-05-20 21:15:05
2026-05-20 | DOCKET/PTB/05-2026/03959 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 701 | 2026-05-20 21:24:54
2026-05-20 | DOCKET/PTB/05-2026/03960 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-05-20 21:52:06
2026-05-20 | DOCKET/PTB/05-2026/03961 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-05-20 22:06:44
2026-05-20 | DOCKET/PTB/05-2026/03962 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-05-20 22:14:30
2026-05-20 | DOCKET/PTB/05-2026/03963 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-05-20 22:23:43
2026-05-20 | DOCKET/PTB/05-2026/03964 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 782 | 2026-05-20 22:36:04
2026-05-20 | DOCKET/PTB/05-2026/03965 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 894 | 2026-05-20 22:51:10
2026-05-20 | DOCKET/PTB/05-2026/03966 | PTRPWJ / RIGID PAV - 13616 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-05-20 22:57:32
2026-05-20 | DOCKET/PTB/05-2026/03922 | WIKA - ADHI JO / DINDING A1 STG.2 OP 8 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 967 | 2026-05-20 13:06:48
2026-05-20 | DOCKET/PTB/05-2026/03923 | WIKA - ADHI JO / DINDING A1 STG.2 OP 8 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 701 | 2026-05-20 13:11:42
2026-05-20 | DOCKET/PTB/05-2026/03924 | WIKA - ADHI JO / DINDING A1 STG.2 OP 8 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-05-20 13:18:46
2026-05-20 | DOCKET/PTB/05-2026/03925 | WIKA - ADHI JO / DINDING A1 STG.2 OP 8 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 813 | 2026-05-20 13:26:00
2026-05-20 | DOCKET/PTB/05-2026/03926 | WIKA - ADHI JO / DINDING A1 STG.2 OP 8 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 687 | 2026-05-20 13:35:05
2026-05-20 | DOCKET/PTB/05-2026/03927 | WIKA - ADHI JO / DINDING A1 STG.2 OP 8 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 944 | 2026-05-20 13:42:35
2026-05-20 | DOCKET/PTB/05-2026/03928 | WIKA - ADHI JO / DINDING A1 STG.2 OP 8 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-05-20 13:49:32
2026-05-20 | DOCKET/PTB/05-2026/03929 | WIKA - ADHI JO / DINDING A1 STG.2 OP 8 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 880 | 2026-05-20 13:58:36
2026-05-20 | DOCKET/PTB/05-2026/03930 | WIKA - ADHI JO / DINDING A1 STG.2 OP 8 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 782 | 2026-05-20 14:30:01
2026-05-20 | DOCKET/PTB/05-2026/03933 | WIKA - ADHI JO / LC A2 OP 8 / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | EGI | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 701 | 2026-05-20 15:26:55
2026-05-20 | DOCKET/PTB/05-2026/03934 | WIKA - ADHI JO / PARAPET W8H - AW1 PS 17 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-05-20 16:14:25
2026-05-20 | DOCKET/PTB/05-2026/03937 | WIKA - ADHI JO / PARAPET W8H - AW1 PS 17 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 813 | 2026-05-20 16:49:36
2026-05-20 | DOCKET/PTB/05-2026/03941 | WIKA - ADHI JO / PARAPET W8H - AW1 PS 17 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | AGUS | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-05-20 17:56:04