## Sheet1
Tanggal | No. Docket | Kontraktor | Nama Proyek | Homebase | Nama Mutu | Slump | TM | Waktu Kirim
2026-05-23 | DOCKET/PTB/05-2026/04059 | HK - JAKON JO / PH GRID B15 & 16 EJ PS16A / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 944 | 2026-05-23 09:09:03
2026-05-23 | DOCKET/PTB/05-2026/04060 | HK - JAKON JO / PH GRID B15 & 16 EJ PS16A / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-05-23 09:14:47
2026-05-23 | DOCKET/PTB/05-2026/04061 | HK - JAKON JO / PH GRID B15 & 16 EJ PS16A / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 880 | 2026-05-23 09:27:08
2026-05-23 | DOCKET/PTB/05-2026/04062 | HK - JAKON JO / PH GRID B15 & 16 EJ PS16A / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 782 | 2026-05-23 09:35:10
2026-05-23 | DOCKET/PTB/05-2026/04063 | HK - JAKON JO / PH GRID B15 & 16 EJ PS16A / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 967 | 2026-05-23 09:46:47
2026-05-23 | DOCKET/PTB/05-2026/04064 | HK - JAKON JO / PH GRID B15 & 16 EJ PS16A / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | TAUFIQ | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 687 | 2026-05-23 12:33:33
2026-05-23 | DOCKET/PTB/05-2026/04095 | PHWM / BOREPILE BP 04/A1 / FC 30 / AD PTB | Proyek Pembangunan Jalan Tol Akses Patimban Paket II | AGUS | Fc-30 NFA | Slump 18.0 +2.0/-2.0 | TM 880 | 2026-05-23 20:55:46
2026-05-23 | DOCKET/PTB/05-2026/04096 | PHWM / BOREPILE BP 04/A1 / FC 30 / AD PTB | Proyek Pembangunan Jalan Tol Akses Patimban Paket II | AGUS | Fc-30 NFA | Slump 18.0 +2.0/-2.0 | TM 894 | 2026-05-23 21:03:00
2026-05-23 | DOCKET/PTB/05-2026/04065 | PHWM / BOREPILE BP P05/A2 / FC 30 / AD PTB | Proyek Pembangunan Jalan Tol Akses Patimban Paket II | AGUS | Fc-30 NFA | Slump 18.0 +2.0/-2.0 | TM 590 | 2026-05-23 12:36:30
2026-05-23 | DOCKET/PTB/05-2026/04066 | PHWM / BOREPILE BP P05/A2 / FC 30 / AD PTB | Proyek Pembangunan Jalan Tol Akses Patimban Paket II | AGUS | Fc-30 NFA | Slump 18.0 +2.0/-2.0 | TM 894 | 2026-05-23 12:44:12
2026-05-23 | DOCKET/PTB/05-2026/04067 | PHWM / BOREPILE BP P05/A2 / FC 30 / AD PTB | Proyek Pembangunan Jalan Tol Akses Patimban Paket II | AGUS | Fc-30 NFA | Slump 18.0 +2.0/-2.0 | TM 813 | 2026-05-23 12:57:22
2026-05-23 | DOCKET/PTB/05-2026/04091 | PTRPWJ / PC SLAB PAV - / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 813 | 2026-05-23 19:31:41
2026-05-23 | DOCKET/PTB/05-2026/04094 | PTRPWJ / PC SLAB PAV - / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 701 | 2026-05-23 20:46:54
2026-05-23 | DOCKET/PTB/05-2026/04102 | PTRPWJ / PC SLAB PAV - / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 944 | 2026-05-23 22:46:14
2026-05-23 | DOCKET/PTB/05-2026/04079 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 590 | 2026-05-23 16:33:46
2026-05-23 | DOCKET/PTB/05-2026/04080 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-05-23 16:43:05
2026-05-23 | DOCKET/PTB/05-2026/04083 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-05-23 17:09:19
2026-05-23 | DOCKET/PTB/05-2026/04084 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-05-23 17:30:11
2026-05-23 | DOCKET/PTB/05-2026/04085 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 701 | 2026-05-23 17:38:21
2026-05-23 | DOCKET/PTB/05-2026/04086 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-05-23 17:45:15
2026-05-23 | DOCKET/PTB/05-2026/04087 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-05-23 17:52:14
2026-05-23 | DOCKET/PTB/05-2026/04088 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 894 | 2026-05-23 18:03:19
2026-05-23 | DOCKET/PTB/05-2026/04089 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-05-23 19:08:16
2026-05-23 | DOCKET/PTB/05-2026/04090 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-05-23 19:15:08
2026-05-23 | DOCKET/PTB/05-2026/04092 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 782 | 2026-05-23 20:31:20
2026-05-23 | DOCKET/PTB/05-2026/04093 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | NANDA | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-05-23 20:36:13
2026-05-23 | DOCKET/PTB/05-2026/04097 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-05-23 21:11:01
2026-05-23 | DOCKET/PTB/05-2026/04098 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-05-23 21:17:12
2026-05-23 | DOCKET/PTB/05-2026/04099 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-05-23 21:47:55
2026-05-23 | DOCKET/PTB/05-2026/04100 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-05-23 21:54:14
2026-05-23 | DOCKET/PTB/05-2026/04101 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 782 | 2026-05-23 22:02:34
2026-05-23 | DOCKET/PTB/05-2026/04103 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 701 | 2026-05-23 22:50:57
2026-05-23 | DOCKET/PTB/05-2026/04104 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-05-23 22:59:00
2026-05-23 | DOCKET/PTB/05-2026/04105 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-05-23 23:32:31
2026-05-23 | DOCKET/PTB/05-2026/04106 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-05-23 23:35:14
2026-05-23 | DOCKET/PTB/05-2026/04107 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 782 | 2026-05-23 23:46:30
2026-05-23 | DOCKET/PTB/05-2026/04108 | PTRPWJ / RIGID PAV - 13619 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-05-23 23:57:23
2026-05-23 | DOCKET/PTB/05-2026/04054 | TATA / K 400 / AD PTB | VINFAST INDONESIA FACTORY (RC PHASE 2) | DENI | K-400 NFA | Slump 12.0 +1.5/-1.5 | TM 880 | 2026-05-23 01:11:06
2026-05-23 | DOCKET/PTB/05-2026/04055 | TATA / K 400 / AD PTB | VINFAST INDONESIA FACTORY (RC PHASE 2) | DENI | K-400 NFA | Slump 12.0 +1.5/-1.5 | TM 782 | 2026-05-23 01:14:59
2026-05-23 | DOCKET/PTB/05-2026/04056 | TATA / K 400 / AD PTB | VINFAST INDONESIA FACTORY (RC PHASE 2) | DENI | K-400 NFA | Slump 12.0 +1.5/-1.5 | TM 967 | 2026-05-23 01:22:57
2026-05-23 | DOCKET/PTB/05-2026/04057 | TATA / K 400 / AD PTB | VINFAST INDONESIA FACTORY (RC PHASE 2) | DENI | K-400 NFA | Slump 12.0 +1.5/-1.5 | TM 813 | 2026-05-23 01:28:54
2026-05-23 | DOCKET/PTB/05-2026/04058 | TATA / K 400 / AD PTB | VINFAST INDONESIA FACTORY (RC PHASE 2) | DENI | K-400 NFA | Slump 12.0 +1.5/-1.5 | TM 701 | 2026-05-23 01:36:40
2026-05-23 | DOCKET/PTB/05-2026/04071 | WIKA - ADHI JO / BP P1- I1 MB 21 / CLASS B-2 SCC / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 880 | 2026-05-23 15:00:54
2026-05-23 | DOCKET/PTB/05-2026/04072 | WIKA - ADHI JO / BP P1- I1 MB 21 / CLASS B-2 SCC / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 590 | 2026-05-23 15:07:15
2026-05-23 | DOCKET/PTB/05-2026/04073 | WIKA - ADHI JO / BP P1- I1 MB 21 / CLASS B-2 SCC / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 944 | 2026-05-23 15:14:44
2026-05-23 | DOCKET/PTB/05-2026/04074 | WIKA - ADHI JO / BP P1- I1 MB 21 / CLASS B-2 SCC / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 852 | 2026-05-23 15:22:55
2026-05-23 | DOCKET/PTB/05-2026/04075 | WIKA - ADHI JO / BP P1- I1 MB 21 / CLASS B-2 SCC / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 967 | 2026-05-23 15:39:12
2026-05-23 | DOCKET/PTB/05-2026/04076 | WIKA - ADHI JO / BP P1- I1 MB 21 / CLASS B-2 SCC / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 687 | 2026-05-23 16:04:57
2026-05-23 | DOCKET/PTB/05-2026/04077 | WIKA - ADHI JO / BP P1- I1 MB 21 / CLASS B-2 SCC / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 813 | 2026-05-23 16:12:31
2026-05-23 | DOCKET/PTB/05-2026/04078 | WIKA - ADHI JO / BP P1- I1 MB 21 / CLASS B-2 SCC / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 880 | 2026-05-23 16:22:33
2026-05-23 | DOCKET/PTB/05-2026/04081 | WIKA - ADHI JO / BP P1- I1 MB 21 / CLASS B-2 SCC / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class C-1 NFA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-05-23 16:48:12
2026-05-23 | DOCKET/PTB/05-2026/04082 | WIKA - ADHI JO / BP P1- I1 MB 21 / CLASS B-2 SCC / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 782 | 2026-05-23 17:01:49
2026-05-23 | DOCKET/PTB/05-2026/04068 | WIKA - ADHI JO / CROSSDRAIN STA 35+700 / CLASS C / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class C-1 NFA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-05-23 14:03:47
2026-05-23 | DOCKET/PTB/05-2026/04069 | WIKA - ADHI JO / CROSSDRAIN STA 35+700 / CLASS C / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class C-1 NFA | Slump 12.0 +2.0/-2.0 | TM 967 | 2026-05-23 14:16:21
2026-05-23 | DOCKET/PTB/05-2026/04070 | WIKA - ADHI JO / CROSSDRAIN STA 35+700 / CLASS C / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | TAUFIQ | Class C-1 NFA | Slump 12.0 +2.0/-2.0 | TM 782 | 2026-05-23 14:37:01