## Sheet1
Tanggal | No. Docket | Kontraktor | Nama Proyek | Homebase | Nama Mutu | Slump | TM | Waktu Kirim
2026-06-19 | DOCKET/PTB/06-2026/05843 | HK - JAKON JO / LC PLATFORM L11 - L15 OP7 / CLASS E / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | EGI | Class E-1 FA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-06-19 08:45:25
2026-06-19 | DOCKET/PTB/06-2026/05844 | HK - JAKON JO / LC PLATFORM L11 - L15 OP7 / CLASS E / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | EGI | Class E-1 FA | Slump 12.0 +2.0/-2.0 | TM 880 | 2026-06-19 08:50:41
2026-06-19 | DOCKET/PTB/06-2026/05845 | HK - JAKON JO / LC PLATFORM L11 - L15 OP7 / CLASS E / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | EGI | Class E-1 FA | Slump 12.0 +2.0/-2.0 | TM 813 | 2026-06-19 09:03:22
2026-06-19 | DOCKET/PTB/06-2026/05847 | HK - JAKON JO / PILECAPE ABT1 BRIDGE OP7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-06-19 09:57:54
2026-06-19 | DOCKET/PTB/06-2026/05848 | HK - JAKON JO / PILECAPE ABT1 BRIDGE OP7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 967 | 2026-06-19 10:21:53
2026-06-19 | DOCKET/PTB/06-2026/05849 | HK - JAKON JO / PILECAPE ABT1 BRIDGE OP7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 944 | 2026-06-19 10:29:12
2026-06-19 | DOCKET/PTB/06-2026/05850 | HK - JAKON JO / PILECAPE ABT1 BRIDGE OP7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 701 | 2026-06-19 10:29:54
2026-06-19 | DOCKET/PTB/06-2026/05851 | HK - JAKON JO / PILECAPE ABT1 BRIDGE OP7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 687 | 2026-06-19 10:52:26
2026-06-19 | DOCKET/PTB/06-2026/05852 | HK - JAKON JO / PILECAPE ABT1 BRIDGE OP7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 900 | 2026-06-19 11:11:05
2026-06-19 | DOCKET/PTB/06-2026/05855 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 631 | 2026-06-19 12:49:30
2026-06-19 | DOCKET/PTB/06-2026/05856 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-06-19 13:05:38
2026-06-19 | DOCKET/PTB/06-2026/05858 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 813 | 2026-06-19 13:18:25
2026-06-19 | DOCKET/PTB/06-2026/05867 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 900 | 2026-06-19 15:03:31
2026-06-19 | DOCKET/PTB/06-2026/05868 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 687 | 2026-06-19 15:17:07
2026-06-19 | DOCKET/PTB/06-2026/05876 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 782 | 2026-06-19 16:59:05
2026-06-19 | DOCKET/PTB/06-2026/05887 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DATA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 967 | 2026-06-19 19:01:08
2026-06-19 | DOCKET/PTB/06-2026/05888 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DATA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 782 | 2026-06-19 19:19:36
2026-06-19 | DOCKET/PTB/06-2026/05889 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DATA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 963 | 2026-06-19 19:57:39
2026-06-19 | DOCKET/PTB/06-2026/05891 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DATA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 900 | 2026-06-19 20:12:24
2026-06-19 | DOCKET/PTB/06-2026/05892 | HK - JAKON JO / PILEHEAD GRID 20 - 23 PS16B / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | DATA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 813 | 2026-06-19 20:20:08
2026-06-19 | DOCKET/PTB/06-2026/05832 | HK - JAKON JO / SLAB CAST INSITU GRID R1 - R10 OP 6 STA 32+048 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | ARDIAN | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 967 | 2026-06-19 00:00:01
2026-06-19 | DOCKET/PTB/06-2026/05833 | HK - JAKON JO / SLAB CAST INSITU GRID R1 - R10 OP 6 STA 32+048 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | ARDIAN | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 880 | 2026-06-19 00:00:27
2026-06-19 | DOCKET/PTB/06-2026/05834 | HK - JAKON JO / SLAB CAST INSITU GRID R1 - R10 OP 6 STA 32+048 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | ARDIAN | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 900 | 2026-06-19 00:04:22
2026-06-19 | DOCKET/PTB/06-2026/05835 | HK - JAKON JO / SLAB CAST INSITU GRID R1 - R10 OP 6 STA 32+048 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | ARDIAN | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 701 | 2026-06-19 00:11:33
2026-06-19 | DOCKET/PTB/06-2026/05836 | HK - JAKON JO / SLAB CAST INSITU GRID R1 - R10 OP 6 STA 32+048 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | ARDIAN | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 813 | 2026-06-19 00:22:59
2026-06-19 | DOCKET/PTB/06-2026/05837 | HK - JAKON JO / SLAB CAST INSITU GRID R1 - R10 OP 6 STA 32+048 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | ARDIAN | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 812 | 2026-06-19 00:29:59
2026-06-19 | DOCKET/PTB/06-2026/05839 | HK - JAKON JO / SLAB CAST INSITU GRID R1 - R10 OP 6 STA 32+048 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | ARDIAN | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 766 | 2026-06-19 00:49:42
2026-06-19 | DOCKET/PTB/06-2026/05840 | HK - JAKON JO / SLAB CAST INSITU GRID R1 - R10 OP 6 STA 32+048 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | ARDIAN | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-06-19 02:21:52
2026-06-19 | DOCKET/PTB/06-2026/05842 | PT. INDONAKANO / K 300 / AD PTB | PATIMBAN INTERNATIONAL CAR TERMINAL GARAGE BUILDING | SUGENG | K-300 NFA | Slump 12.0 +2.0/-2.0 | TM 900 | 2026-06-19 08:27:45
2026-06-19 | DOCKET/PTB/06-2026/05846 | PT. INDONAKANO / K 300 / AD PTB | PATIMBAN INTERNATIONAL CAR TERMINAL GARAGE BUILDING | SUGENG | K-300 NFA | Slump 12.0 +2.0/-2.0 | TM 782 | 2026-06-19 09:09:12
2026-06-19 | DOCKET/PTB/06-2026/05853 | PT. INDONAKANO / K 300 / AD PTB | PATIMBAN INTERNATIONAL CAR TERMINAL GARAGE BUILDING | SUGENG | K-300 NFA | Slump 12.0 +2.0/-2.0 | TM 631 | 2026-06-19 11:51:39
2026-06-19 | DOCKET/PTB/06-2026/05860 | PT. INDONAKANO / K 300 / AD PTB | PATIMBAN INTERNATIONAL CAR TERMINAL GARAGE BUILDING | SUGENG | K-300 NFA | Slump 12.0 +2.0/-2.0 | TM 963 | 2026-06-19 13:41:35
2026-06-19 | DOCKET/PTB/06-2026/05875 | PTRPWJ / PC SLAB PAV - 14690 / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 701 | 2026-06-19 16:49:59
2026-06-19 | DOCKET/PTB/06-2026/05878 | PTRPWJ / PC SLAB PAV - 14690 / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 963 | 2026-06-19 17:13:01
2026-06-19 | DOCKET/PTB/06-2026/05883 | PTRPWJ / PC SLAB PAV - 14690 / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 894 | 2026-06-19 18:24:01
2026-06-19 | DOCKET/PTB/06-2026/05885 | PTRPWJ / PC SLAB PAV - 14690 / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 852 | 2026-06-19 18:41:35
2026-06-19 | DOCKET/PTB/06-2026/05886 | PTRPWJ / PC SLAB PAV - 14690 / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 701 | 2026-06-19 18:47:40
2026-06-19 | DOCKET/PTB/06-2026/05863 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-06-19 14:34:32
2026-06-19 | DOCKET/PTB/06-2026/05864 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-06-19 14:42:15
2026-06-19 | DOCKET/PTB/06-2026/05865 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 701 | 2026-06-19 14:47:46
2026-06-19 | DOCKET/PTB/06-2026/05866 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 782 | 2026-06-19 14:56:11
2026-06-19 | DOCKET/PTB/06-2026/05869 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 687 | 2026-06-19 15:19:56
2026-06-19 | DOCKET/PTB/06-2026/05870 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 963 | 2026-06-19 15:36:12
2026-06-19 | DOCKET/PTB/06-2026/05871 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-06-19 15:37:14
2026-06-19 | DOCKET/PTB/06-2026/05872 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 631 | 2026-06-19 16:09:18
2026-06-19 | DOCKET/PTB/06-2026/05873 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-06-19 16:12:26
2026-06-19 | DOCKET/PTB/06-2026/05874 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-06-19 16:30:00
2026-06-19 | DOCKET/PTB/06-2026/05877 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-06-19 17:07:13
2026-06-19 | DOCKET/PTB/06-2026/05879 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 687 | 2026-06-19 17:25:59
2026-06-19 | DOCKET/PTB/06-2026/05880 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 900 | 2026-06-19 17:49:57
2026-06-19 | DOCKET/PTB/06-2026/05881 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-06-19 17:52:32
2026-06-19 | DOCKET/PTB/06-2026/05882 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-06-19 18:12:52
2026-06-19 | DOCKET/PTB/06-2026/05884 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-06-19 18:31:58
2026-06-19 | DOCKET/PTB/06-2026/05890 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | AGUS | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 687 | 2026-06-19 20:04:36
2026-06-19 | DOCKET/PTB/06-2026/05893 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 894 | 2026-06-19 20:37:22
2026-06-19 | DOCKET/PTB/06-2026/05894 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-06-19 20:51:31
2026-06-19 | DOCKET/PTB/06-2026/05895 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 631 | 2026-06-19 20:58:17
2026-06-19 | DOCKET/PTB/06-2026/05896 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-06-19 21:07:33
2026-06-19 | DOCKET/PTB/06-2026/05897 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-06-19 21:31:31
2026-06-19 | DOCKET/PTB/06-2026/05898 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-06-19 21:36:47
2026-06-19 | DOCKET/PTB/06-2026/05899 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 701 | 2026-06-19 21:43:44
2026-06-19 | DOCKET/PTB/06-2026/05900 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-06-19 22:23:32
2026-06-19 | DOCKET/PTB/06-2026/05901 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 963 | 2026-06-19 22:30:20
2026-06-19 | DOCKET/PTB/06-2026/05902 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 687 | 2026-06-19 22:38:55
2026-06-19 | DOCKET/PTB/06-2026/05906 | PTRPWJ / RIGID PAV - 14676 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-06-19 23:26:48
2026-06-19 | DOCKET/PTB/06-2026/05903 | WIKA - ADHI JO / BP P1 1Q MB21 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 631 | 2026-06-19 23:05:50
2026-06-19 | DOCKET/PTB/06-2026/05904 | WIKA - ADHI JO / BP P1 1Q MB21 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 852 | 2026-06-19 23:13:26
2026-06-19 | DOCKET/PTB/06-2026/05905 | WIKA - ADHI JO / BP P1 1Q MB21 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 894 | 2026-06-19 23:18:11
2026-06-19 | DOCKET/PTB/06-2026/05907 | WIKA - ADHI JO / BP P1 1Q MB21 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 967 | 2026-06-19 23:35:02
2026-06-19 | DOCKET/PTB/06-2026/05908 | WIKA - ADHI JO / BP P1 1Q MB21 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 782 | 2026-06-19 23:41:31
2026-06-19 | DOCKET/PTB/06-2026/05909 | WIKA - ADHI JO / BP P1 1Q MB21 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 900 | 2026-06-19 23:48:15
2026-06-19 | DOCKET/PTB/06-2026/05910 | WIKA - ADHI JO / BP P1 1Q MB21 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | ARDIAN | Class B-2 NFA | Slump 55.0 +10.0/-0.0 | TM 944 | 2026-06-19 23:57:33
2026-06-19 | DOCKET/PTB/06-2026/05857 | WIKA - ADHI JO / REPAIR LUBANG BOREPILE / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | EGI | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 880 | 2026-06-19 13:10:45
2026-06-19 | DOCKET/PTB/06-2026/05859 | WIKA - ADHI JO / REPAIR LUBANG BOREPILE / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | EGI | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 701 | 2026-06-19 13:30:41
2026-06-19 | DOCKET/PTB/06-2026/05861 | WIKA - ADHI JO / REPAIR LUBANG BOREPILE / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | EGI | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 782 | 2026-06-19 13:49:22
2026-06-19 | DOCKET/PTB/06-2026/05862 | WIKA - ADHI JO / REPAIR LUBANG BOREPILE / CLASS E / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | EGI | Class E-1 NFA | Slump 12.0 +2.0/-2.0 | TM 944 | 2026-06-19 14:23:51