## Sheet1
Tanggal | No. Docket | Kontraktor | Nama Proyek | Homebase | Nama Mutu | Slump | TM | Waktu Kirim
2026-06-23 | DOCKET/PTB/06-2026/06110 | HK - JAKON JO / BARRIER PARAPET A1 - P1 OP.7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 880 | 2026-06-23 18:55:25
2026-06-23 | DOCKET/PTB/06-2026/06111 | HK - JAKON JO / BARRIER PARAPET A1 - P1 OP.7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 967 | 2026-06-23 19:02:41
2026-06-23 | DOCKET/PTB/06-2026/06118 | HK - JAKON JO / BARRIER PARAPET A1 - P1 OP.7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 631 | 2026-06-23 20:14:25
2026-06-23 | DOCKET/PTB/06-2026/06119 | HK - JAKON JO / BARRIER PARAPET A1 - P1 OP.7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 701 | 2026-06-23 20:23:00
2026-06-23 | DOCKET/PTB/06-2026/06125 | HK - JAKON JO / BARRIER PARAPET A1 - P1 OP.7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 944 | 2026-06-23 21:39:01
2026-06-23 | DOCKET/PTB/06-2026/06128 | HK - JAKON JO / BARRIER PARAPET A1 - P1 OP.7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-06-23 22:04:13
2026-06-23 | DOCKET/PTB/06-2026/06132 | HK - JAKON JO / BARRIER PARAPET A1 - P1 OP.7 / CLASS B-1 / AD PTB | Pembangunan Jalan Tol Akses Patimban Paket 3 | NANDA | Class B-1 FA | Slump 12.0 +2.0/-2.0 | TM 701 | 2026-06-23 22:50:38
2026-06-23 | DOCKET/PTB/06-2026/06109 | PTRPWJ / PC SLAB PAV - / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 701 | 2026-06-23 18:22:49
2026-06-23 | DOCKET/PTB/06-2026/06115 | PTRPWJ / PC SLAB PAV - / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 687 | 2026-06-23 19:48:10
2026-06-23 | DOCKET/PTB/06-2026/06116 | PTRPWJ / PC SLAB PAV - / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 687 | 2026-06-23 19:50:05
2026-06-23 | DOCKET/PTB/06-2026/06122 | PTRPWJ / PC SLAB PAV - / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 963 | 2026-06-23 21:18:50
2026-06-23 | DOCKET/PTB/06-2026/06130 | PTRPWJ / PC SLAB PAV - / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 967 | 2026-06-23 22:34:21
2026-06-23 | DOCKET/PTB/06-2026/06133 | PTRPWJ / PC SLAB PAV - / CLASS G-3 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class G NFA-3 NFA | Slump 8.0 +4.0/-0.0 | TM 852 | 2026-06-23 23:09:21
2026-06-23 | DOCKET/PTB/06-2026/06092 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-06-23 15:05:59
2026-06-23 | DOCKET/PTB/06-2026/06093 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 963 | 2026-06-23 15:11:23
2026-06-23 | DOCKET/PTB/06-2026/06094 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-06-23 15:17:04
2026-06-23 | DOCKET/PTB/06-2026/06095 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-06-23 15:24:04
2026-06-23 | DOCKET/PTB/06-2026/06097 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 900 | 2026-06-23 15:36:24
2026-06-23 | DOCKET/PTB/06-2026/06098 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 687 | 2026-06-23 15:44:09
2026-06-23 | DOCKET/PTB/06-2026/06100 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 894 | 2026-06-23 16:25:26
2026-06-23 | DOCKET/PTB/06-2026/06101 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-06-23 16:33:36
2026-06-23 | DOCKET/PTB/06-2026/06102 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 967 | 2026-06-23 16:41:07
2026-06-23 | DOCKET/PTB/06-2026/06103 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-06-23 16:48:07
2026-06-23 | DOCKET/PTB/06-2026/06104 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 963 | 2026-06-23 16:53:12
2026-06-23 | DOCKET/PTB/06-2026/06105 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 687 | 2026-06-23 17:06:11
2026-06-23 | DOCKET/PTB/06-2026/06106 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 631 | 2026-06-23 17:14:21
2026-06-23 | DOCKET/PTB/06-2026/06107 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | DENI | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-06-23 17:18:49
2026-06-23 | DOCKET/PTB/06-2026/06112 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 894 | 2026-06-23 19:22:54
2026-06-23 | DOCKET/PTB/06-2026/06113 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-06-23 19:27:13
2026-06-23 | DOCKET/PTB/06-2026/06114 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-06-23 19:43:47
2026-06-23 | DOCKET/PTB/06-2026/06117 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 944 | 2026-06-23 19:57:51
2026-06-23 | DOCKET/PTB/06-2026/06120 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 900 | 2026-06-23 20:46:58
2026-06-23 | DOCKET/PTB/06-2026/06121 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-06-23 21:09:23
2026-06-23 | DOCKET/PTB/06-2026/06123 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-06-23 21:25:46
2026-06-23 | DOCKET/PTB/06-2026/06124 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 852 | 2026-06-23 21:26:38
2026-06-23 | DOCKET/PTB/06-2026/06126 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 687 | 2026-06-23 21:47:46
2026-06-23 | DOCKET/PTB/06-2026/06127 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 880 | 2026-06-23 21:53:20
2026-06-23 | DOCKET/PTB/06-2026/06129 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 631 | 2026-06-23 22:11:33
2026-06-23 | DOCKET/PTB/06-2026/06131 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 813 | 2026-06-23 22:43:31
2026-06-23 | DOCKET/PTB/06-2026/06134 | PTRPWJ / RIGID PAV - 15269 / CLASS A-2 / AD PTB | Patimban Port Development Project Package 6 : Container Terminal No.2 Construction | TAUFIQ | Class A-2 NFA | Slump 5.0 +5.0/-0.0 | TM 963 | 2026-06-23 23:54:53
2026-06-23 | DOCKET/PTB/06-2026/06096 | WIKA - ADHI JO / MEDIAN DRAIN RAMP 5 / CLASS C / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class C-1 NFA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-06-23 15:29:23
2026-06-23 | DOCKET/PTB/06-2026/06108 | WIKA - ADHI JO / MEDIAN DRAIN RAMP 5 / CLASS C / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class C-1 NFA | Slump 12.0 +2.0/-2.0 | TM 900 | 2026-06-23 17:55:03
2026-06-23 | DOCKET/PTB/06-2026/06087 | WIKA - ADHI JO / PLAT INJAK IC 03 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 813 | 2026-06-23 14:01:12
2026-06-23 | DOCKET/PTB/06-2026/06088 | WIKA - ADHI JO / PLAT INJAK IC 03 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 900 | 2026-06-23 14:07:20
2026-06-23 | DOCKET/PTB/06-2026/06089 | WIKA - ADHI JO / PLAT INJAK IC 03 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 852 | 2026-06-23 14:14:05
2026-06-23 | DOCKET/PTB/06-2026/06090 | WIKA - ADHI JO / PLAT INJAK IC 03 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 687 | 2026-06-23 14:22:58
2026-06-23 | DOCKET/PTB/06-2026/06091 | WIKA - ADHI JO / PLAT INJAK IC 03 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-06-23 14:29:08
2026-06-23 | DOCKET/PTB/06-2026/06099 | WIKA - ADHI JO / PLAT INJAK IC 03 / CLASS B-1 / AD PTB | JALAN TOL AKSES PATIMBAN PAKET 4 | DATA | Class B-1 NFA | Slump 12.0 +2.0/-2.0 | TM 894 | 2026-06-23 15:50:10